AI Agent & Chatbot Studio

End-to-End Implementation Plan (AI-Driven Delivery)

A phased, buildable roadmap to design, develop, and deploy a multi-tenant platform for creating agents, chatbots, and automated workflows — built with AI at every stage.

Prepared for: CIOG AI & Analytics Team, Movate Technologies

Prepared with Microsoft Copilot

# Contents

# 1. Executive Summary

This document lays out an end-to-end implementation plan for building an internal AI Agent & Chatbot Studio — a single, no-code/low-code platform where teams can create AI agents, deploy chatbots, and automate workflows grounded in Movate's own data. It consolidates the direction already proven in our prototypes (FlowForge workflow canvas, the AI Studio demo) and the MedhAI Lyzer runtime reference into a delivery plan the team can execute.

The plan is deliberately AI-driven: generative AI is used not only inside the product (agents, RAG, orchestration) but also throughout delivery — for code generation, test creation, documentation, and evaluation — so a small team can ship a large surface area quickly.

Objective: Deliver a production-ready, multi-tenant studio that lets business teams build grounded AI agents and automated workflows in minutes, with enterprise-grade governance, security, and observability aligned to ISO/IEC 42001.

Target outcome by end of plan

- A working studio with Agent Builder, Knowledge Hub (RAG), visual Workflow Builder, Playground, Deployment Center, and Analytics.

- Multi-tenant, SSO-secured, and governed — reusing our Azure OpenAI + Azure AI Search + pgvector stack.

- Delivered over ~6 months across 6 phases using 2-week agile sprints.

# 2. Objectives, Scope & Success Criteria

## 2.1 Business Objectives

- Reduce time-to-build for internal AI agents from weeks to hours via a no-code studio.

- Centralise agent creation, knowledge grounding, deployment, and monitoring in one governed platform.

- Move beyond the limits we hit with Copilot Studio (prompt control, scoring logic, multi-agent orchestration, large-document RAG) by owning the runtime.

- Support reuse: templates, shared connectors, and a marketplace of ready agents.

## 2.2 In Scope

- Agent & chatbot builder, knowledge/RAG pipeline, visual workflow builder, playground, multi-channel deployment (Web, API, Teams), analytics, governance and admin.

## 2.3 Out of Scope (Phase 1)

- Voice/IVR channels, mobile SDK, external customer-facing commerce flows, and fine-tuning of custom models — planned as later increments.

## 2.4 Success Criteria

| Dimension | Target |
| --- | --- |
| Time to build an agent | < 30 minutes from blank to tested in playground |
| RAG answer quality | ≥ 90% grounded accuracy on curated eval set; citations on every answer |
| Workflow reliability | ≥ 99% successful executions; automatic retry + human-in-the-loop gates |
| Latency | P95 chat response < 3s; streaming first token < 1s |
| Adoption | ≥ 5 business teams and 20+ live agents within 60 days of GA |
| Governance | 100% of agents logged, access-controlled, and audit-ready (ISO/IEC 42001) |

# 3. Solution Architecture

The studio follows the layered agentic architecture our team standardised on, mapped to concrete Azure services. Each layer is independently buildable and testable.

| Layer | Responsibility | Technology |
| --- | --- | --- |
| Presentation | Studio UI, chat widget, playground, dashboards | Next.js / React, React Flow (workflow canvas), Tailwind |
| API / Gateway | Auth, routing, rate limiting, tenant scoping | FastAPI, Azure API Management, Entra ID (OIDC/SSO) |
| Orchestration | Workflow engine, agent routing, human approval | LangGraph StateGraph, Celery + Redis, checkpointer |
| Agent & Reasoning | Planning, tool selection, multi-agent collaboration | LangGraph, LangChain, supervisor/worker pattern |
| Memory | Session, long-term, and semantic memory | Redis (short-term), PostgreSQL + pgvector (long-term) |
| Knowledge (RAG) | Ingestion, chunking, embeddings, hybrid search | Azure AI Search (hybrid+semantic), pgvector, Doc Intelligence |
| Model | LLMs, embeddings, vision, speech | Azure OpenAI (GPT-4o family), text-embedding-3, model router |
| Tool / Connectors | SharePoint, SQL, REST, email, CRM, ITSM | MCP connectors, custom tool registry, Power Automate |
| Data & Storage | Documents, state, logs, metadata | Azure Blob, PostgreSQL 15, Log Analytics |
| Infrastructure | Compute, secrets, CI/CD, scaling | Azure Container Apps/AKS, Key Vault, GitHub Actions |

Cross-cutting: Security, guardrails (PII masking, prompt-injection defence, content filters), observability (traces, metrics, logs), governance (audit trails, versioning, RBAC), evaluation, and cost management span every layer.

# 4. Technology Stack & AI-Assisted Delivery

## 4.1 Core Stack

| Area | Choice |
| --- | --- |
| Frontend | Next.js, React, React Flow, TypeScript, Tailwind |
| Backend | Python, FastAPI, SQLAlchemy (async), Pydantic |
| Agent runtime | LangGraph + LangChain on Azure OpenAI |
| Async / jobs | Celery, Redis, Flower |
| Data | PostgreSQL 15 + pgvector, Azure Blob, Azure AI Search |
| Auth | Microsoft Entra ID (OIDC, SSO, MFA), RBAC |
| DevOps | GitHub, GitHub Actions CI/CD, Docker, Azure Container Apps |
| Observability | Azure Monitor / App Insights, LangSmith tracing, Sentry |

## 4.2 Where AI Accelerates Delivery

AI is applied to the build process itself, so the team ships faster with higher quality:

- Code generation: GitHub Copilot / LLMs scaffold FastAPI routes, React components, connectors, and LangGraph nodes from specs.

- Test generation: AI drafts unit, integration, and eval tests; regression suites for RAG and agents.

- Synthetic eval data: Generate Q&A pairs and edge cases to benchmark grounding accuracy.

- Documentation: Auto-generate API docs, user guides, and admin runbooks from code and configs.

- Prompt & agent design: AI helps author system prompts, tool schemas, and workflow templates.

# 5. Phased Implementation Roadmap

Delivery is split into six phases over roughly 24 weeks (12 two-week sprints). Each phase ends with a demoable, testable increment.

| Phase | Focus | Duration | Key Outcome |
| --- | --- | --- | --- |
| Phase 0 | Discovery & Foundations | 2 weeks | Architecture signed off, environments & CI/CD ready |
| Phase 1 | Core Platform & Agent Builder | 4 weeks | Create, configure & test a grounded agent |
| Phase 2 | Knowledge Hub & RAG | 4 weeks | Ingestion + hybrid RAG with citations |
| Phase 3 | Workflow Builder & Orchestration | 4 weeks | Visual multi-step flows with human-in-the-loop |
| Phase 4 | Deployment, Channels & Analytics | 4 weeks | Publish to Web/API/Teams; usage dashboards |
| Phase 5 | Governance, Security & Hardening | 3 weeks | RBAC, audit, guardrails, ISO 42001 evidence |
| Phase 6 | Pilot, Scale & GA | 3 weeks | Pilot with business teams; production go-live |

## Phase 0 — Discovery & Foundations (Weeks 1–2)

Goals

- Confirm scope, personas, and top 3 pilot use cases (e.g., HR Policy, IT support, invoice triage).

- Finalise architecture, data model, and multi-tenant strategy.

Tasks

- Set up Azure subscriptions, resource groups, Key Vault, networking.

- Stand up repos, CI/CD pipelines, Dev/Test/Prod environments.

- Define tenant/org schema, RBAC roles, and coding standards.

Deliverables

- Signed-off architecture & ADrs, provisioned environments, working CI/CD skeleton.

## Phase 1 — Core Platform & Agent Builder (Weeks 3–6)

Goals

- Users can create, configure, and test a single grounded agent.

Tasks

- Build API scaffolding (FastAPI), auth (Entra ID SSO), and tenant scoping.

- Agent Builder UI: name, description, base model, system instructions, temperature, guardrails.

- Model layer: Azure OpenAI integration with streaming; model selection & token controls.

- Chat Playground with session memory (Redis) and trace logging.

Deliverables

- End-to-end: create an agent → chat in playground → see traces. Auto-saved drafts.

## Phase 2 — Knowledge Hub & RAG (Weeks 7–10)

Goals

- Ground agents in company data with reliable, cited retrieval.

Tasks

- Document ingestion (PDF/DOCX/CSV/PPTX) via Azure Document Intelligence; chunking pipeline (Celery).

- Embeddings + indexing into Azure AI Search (hybrid + semantic) and pgvector.

- Retrieval with query rewriting, ranking, and citation of sources.

- Knowledge versioning, per-agent knowledge scoping, and access policies.

Deliverables

- Upload docs → indexed → agent answers with citations at ≥90% grounded accuracy on the eval set.

## Phase 3 — Workflow Builder & Orchestration (Weeks 11–14)

Goals

- Chain triggers, agents, and actions into automated, reliable flows.

Tasks

- React Flow canvas (evolve FlowForge): drag nodes, connect edges, configure per-node properties.

- Serialise graph to JSON; dynamically build LangGraph StateGraph at runtime.

- Node types: Trigger, AI Agent, Tool/Action, Condition, Human Approval, Notify.

- Durable execution: checkpointer, retries, interrupt-before for human sign-off; execution logs & replay.

Deliverables

- Build & run a multi-step workflow (e.g., invoice triage) with a human approval gate and full trace.

## Phase 4 — Deployment, Channels & Analytics (Weeks 15–18)

Goals

- Publish agents across channels and monitor them centrally.

Tasks

- Deployment Center: web chat widget (embed script), secure REST/streaming API endpoint, Teams bot.

- Tenant-scoped API keys, versioning, and staged rollout (draft → test → live).

- Analytics dashboard: conversations, resolution rate, latency, token usage, and cost.

Deliverables

- One-click publish to Web + API + Teams; live analytics with cost and quality metrics.

## Phase 5 — Governance, Security & Hardening (Weeks 19–21)

Goals

- Make the platform enterprise-safe and audit-ready.

Tasks

- RBAC & permissions, org/workspace management, SSO/SCIM, per-tenant quotas.

- Guardrails: PII masking, content filters, prompt-injection & jailbreak detection.

- Audit logging, event logs, data residency, backup/DR; security & load testing.

- Assemble ISO/IEC 42001 evidence (objectives, risk register, validation, monitoring).

Deliverables

- Hardened, governed platform with complete audit trails and compliance pack.

## Phase 6 — Pilot, Scale & GA (Weeks 22–24)

Goals

- Validate with real users and go to production.

Tasks

- Onboard 3–5 pilot teams; migrate existing Copilot Studio agents where beneficial.

- Collect feedback, tune prompts/RAG, run UAT and performance tuning.

- Production go-live, runbooks, support model, and training.

Deliverables

- GA release with onboarded teams, live agents, and an operating support model.

# 6. Team, Roles & Effort

| Role | Responsibility | Allocation |
| --- | --- | --- |
| Tech Lead / Architect | Architecture, standards, reviews | 1 (full) |
| Backend Engineers | API, agents, RAG, orchestration | 2 |
| Frontend Engineer | Studio UI, workflow canvas, playground | 1–2 |
| Data / AI Engineer | Ingestion, embeddings, evaluation | 1 |
| DevOps Engineer | CI/CD, Azure infra, security | 1 (shared) |
| Product / QA | Backlog, UAT, eval, docs (AI-assisted) | 1 |

Lean-team note: Because AI accelerates code, tests, and docs, a 5–7 person team can deliver this scope. Use LLMs only where language understanding is needed; keep deterministic logic (scoring, routing, quotas) in code.

# 7. Delivery Cadence & Governance

- Methodology: Agile, 2-week sprints (12 sprints total).

- Ceremonies: Sprint Planning, Daily Standup (15 min), Sprint Review (demo), Retrospective.

- Definition of Done: coded, AI + human reviewed, tested (incl. eval), documented, deployed to Test.

- Steering: bi-weekly stakeholder review tied to phase exit criteria.

# 8. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| LLM inconsistency / hallucination | High | Strong RAG grounding, citations, schema-constrained outputs, eval gates |
| Large-document RAG quality (past pain point) | High | Hybrid + semantic search, query rewriting, chunk tuning, re-ranking |
| Cost overruns (tokens) | Medium | Model routing, caching, budget limits, per-tenant quotas |
| Scope creep | Medium | Phase gates, MVP-first, defer voice/mobile to later increments |
| Security & data leakage | High | RBAC, PII masking, guardrails, audit logs, data residency |
| Over-automation without oversight | Medium | Human-in-the-loop approval gates on sensitive actions |

# 9. Immediate Next Steps

- Approve scope, architecture, and the three pilot use cases.

- Provision Azure environments, repos, and CI/CD (Phase 0).

- Stand up the Agent Builder + Playground vertical slice (Phase 1).

- Curate the evaluation dataset early to measure RAG quality from day one.

Recommendation: Start with a single high-value, well-scoped agent (e.g., HR Policy or IT support) as the reference implementation, then generalise the studio around it. This de-risks delivery and gives an early adoption win.